# EWTSS v2 - Work Breakdown Structure

For Zoho Projects import. Prepared 2026-06-29 - draft for PM review. PROPRIETARY & CONFIDENTIAL - internal distribution only.

Derived from the design docs: v2-execution-plan.md (team, 17-week / 7-phase structure, per-person ownership, critical path, integration gates) and design-backlog.md (Milestone-1 design items B1.x + documentation deliverables). One task per row.

## Owner legend

The repo names people by role ID, not by name. Map A-G and the leads to real people before scheduling.

| ID | Role |
| --- | --- |
| F | drs-server lead (Senior Python) |
| A | drs-bridge Python + C# scenario-publisher integration |
| B | SG (C# specialist) |
| C | C++ parser libraries |
| D | cross-stack lead - architect, integration-test owner, infra/packaging |
| E | drs-server REST/auth/reports (React dev, cross-trained to Python) |
| G | DRS webapp lead (React) |
| PL / AL | project lead / architecture lead |
| Ops / Sec | ops-lab lead / security tester |

## Work breakdown structure

| Task List | Task Name | Parent Task | Owner | Duration (days) | Dependency | Description |
| --- | --- | --- | --- | --- | --- | --- |
| M1 - Design & Contracts | Detailed UX wireframes |  | PL + AL | 25 |  | B1.1 - RFQ M1 deliverable (Mock UI Wireframes for SG and DRS Applications). Parent for the two surface tracks. |
| M1 - Design & Contracts | SG-side UX wireframes | Detailed UX wireframes | B | 15 |  | B1.1 SG surfaces: login/dashboard, GIS authoring (gaming area/AOP/FEBA/VA), scenario tree, entity edit panels, map tools, EW library, environment config, compute/exercise control, telemetry panels, reports, admin. |
| M1 - Design & Contracts | DRS-side UX wireframes | Detailed UX wireframes | G | 10 |  | B1.1 DRS surfaces: dashboard + health indicators, per-variant monitor-scan, sent/receive logs, LRU/subsystem/comm-link health, IP config, per-variant control, Kafka consumer health. |
| M1 - Design & Contracts | Typed-entity DTO spec |  | B + AL | 4 |  | B1.25 - Transmitter/Receiver/Antenna field definitions, ranges, relationships. Build-blocker for B. |
| M1 - Design & Contracts | Blue/Red Line entity mapping decision |  | AL + B | 2 |  | B1.15 - map RFQ Blue/Red Line vocabulary onto v2 STK entity types; likely a side attribute (Blue/Red/Neutral) + color coding. New ADR. |
| M1 - Design & Contracts | RBAC role definitions |  | E + AL | 3 |  | B1.16 - SG Operator / DRS Engineer / Admin roles; per-role feature/permission grants; shared RBAC store. |
| M1 - Design & Contracts | Auth lifecycle flow designs |  | E + B + G | 5 | RBAC role definitions | B1.17 - sequence-diagram logout, JWT refresh, lockout, password change/reset, session timeout, re-auth on destructive actions, token revocation, concurrent-session policy. |
| M1 - Design & Contracts | Report template catalogue |  | PL + E + B | 3 |  | B1.11 - report-template inventory (per-exercise summary, access-interval, post-exercise, mission summary) + per-template field-to-TimescaleDB mapping. |
| M1 - Design & Contracts | CC integration API surface |  | AL + PL | 5 |  | B1.4 - define v2-decidable exposed surface (exercise-lifecycle topics, health push). EXTERNALLY BLOCKED on client CC requirements; design what v2 controls unilaterally. |
| M1 - Design & Contracts | Security design baseline |  | D + E | 5 |  | B1.27 - threat model, data classification, AuthN/AuthZ posture, audit-log integrity, transport/secrets/supply-chain. Spec landed 2026-05-31; tracks the bar code review validates against. |
| M1 - Design & Contracts | Contract artefact freeze |  | F + B + D | 5 | Typed-entity DTO spec | B1.26 - freeze OpenAPI (incl. webapp endpoints) + scenario/DTO shapes + Kafka schemas. Partly done (contracts/ scaffolded); freeze when OpenAPI complete + B1.25 landed + consumers sign off. |
| Infrastructure & Platform | Kafka KRaft broker setup |  | D + A | 3 |  | Native single-node Kafka 3.x KRaft on WS2 (no Docker). infrastructure/kafka/. Largely shipped. |
| Infrastructure & Platform | Kafka topic provisioning scripts |  | D | 2 | Kafka KRaft broker setup | Idempotent control-plane topic provisioner; topic naming signed off at contracts gate. |
| Infrastructure & Platform | TimescaleDB schema + hypertables |  | D + F | 3 |  | PostgreSQL 16 + TimescaleDB 2.x; measurements hypertable + write-batching schema; hypertable init scripts. |
| Infrastructure & Platform | DB foundation (SQLAlchemy + Alembic) |  | F | 3 | TimescaleDB schema + hypertables | Async SQLAlchemy 2.0 + Alembic + asyncpg foundation in drs-server. Shipped for roster store. |
| Infrastructure & Platform | Time synchronization service (NTP) |  | AL + D | 8 |  | B1.3 - Meinberg NTP SG<->WS2 (<=10ms); three-tier SyncStateEngine + Kafka publisher; SG banner host + exercise gating + SYNC_LOST auto-pause. Mostly implemented; Phase 7 load test open. |
| Infrastructure & Platform | NTP install scripts + lab acceptance | Time synchronization service (NTP) | Ops + D | 3 |  | B1.20 - vendor Meinberg MSI, distribute to air-gap mirror, run sg/ws2 install + smoke on lab hardware, capture offsets. Human-driven; gates B1.3 lab acceptance. |
| Infrastructure & Platform | Windows Service units (NSSM) |  | D | 2 |  | Wrap drs-server / drs-bridge as Windows Services via NSSM/sc.exe. |
| Infrastructure & Platform | Air-gap dependency vendoring process |  | D | 5 |  | B1.18 - packages/ layout, pip download + offline-verify, npm offline cache + Node 22 toolchain, PR-time check. Process documented; binary vendoring deferred to pre-delivery freeze. |
| Infrastructure & Platform | JVM licence decision (Kafka runtime) |  | PL + D | 1 |  | B1.44 - accept OpenJDK/Temurin GPLv2+Classpath-Exception (record rationale) or select alternative. Blocks air-gap packaging of the Kafka runtime. DECISION REQUIRED. |
| Infrastructure & Platform | Polyrepo migration + release manifests |  | D + PL | 4 |  | Repository & release strategy: split into six repos (four service + ewtss-release + ewtss-references), namespaced tags, versioned YAML release manifests, per-repo .claude/CLAUDE.md standard. |
| Infrastructure & Platform | CI bring-up harness |  | D | 3 | Kafka topic provisioning scripts | Native spin-up of Kafka + PostgreSQL + drs-server + drs-bridge for the integration test environment. NOTE: org-hosted CI runners currently paused. |
| drs-server | FastAPI scaffold + lifespan consumers |  | F | 4 | Contract artefact freeze | FastAPI scaffold; async engine + asyncpg pool; lifespan-managed Kafka consumers; first echo consumer. |
| drs-server | Per-variant Kafka consumers to TimescaleDB |  | F | 6 | FastAPI scaffold + lifespan consumers, First-variant C++ parser | Per-variant consumer services (~40 lines each); batched writes (100 msg / 500 ms); manual offset commit only after successful DB write. |
| drs-server | WebSocket fan-out hub |  | F | 5 | Per-variant Kafka consumers to TimescaleDB | Subscribe to Kafka topics, broadcast to subscribed clients; auto-reconnect on consumer crash with exponential backoff. |
| drs-server | Consumer supervisor + health endpoints |  | F | 3 | Per-variant Kafka consumers to TimescaleDB | Consumer supervisor with exponential backoff + restart-count metric; /health/consumers and /health/<variant>/<instance>. |
| drs-server | E Python ramp |  | E | 10 |  | Weeks 1-2 pair with F on drs-server idioms (async SQLAlchemy, asyncpg, Pydantic, FastAPI lifespan). Specialist risk: must complete by week 3. |
| drs-server | REST query endpoints |  | E | 6 | DB foundation (SQLAlchemy + Alembic), E Python ramp | Paginated/time-bounded query endpoints (no query.all()): /measurements, /measurements/export (StreamingResponse), /sessions, /sessions/{id}/stats. |
| drs-server | RBAC + JWT auth |  | E | 8 | RBAC role definitions, REST query endpoints | Users/roles/features/permissions tables + middleware; JWT issuance + refresh; token verify on every mutating route. |
| drs-server | Auth lifecycle endpoints |  | E | 5 | RBAC + JWT auth, Auth lifecycle flow designs | B1.17 server side: /auth/* logout, refresh rotation, lockout, password reset, token-revocation list. |
| drs-server | PDF report generation |  | E | 6 | Report template catalogue, REST query endpoints | WeasyPrint render: scenario summary, access-interval tables, post-exercise report. Not on critical path (ships in maintenance if needed). |
| drs-server | DRS roster store + API |  | E + F | 6 | DB foundation (SQLAlchemy + Alembic) | B1.43 Plan 2a - roster/roster_entry/roster_revision tables, RosterRepository, read/write/export-import REST endpoints. Implemented (PR #2). |
| drs-server | Roster publisher + presence + readiness reconcile |  | E + F | 5 | DRS roster store + API, Kafka topic provisioning scripts | B1.43 Plan 2b - RosterPublisher to compacted drs.roster, PresenceConsumer, POST /exercise/readiness, port allocator. Implemented. |
| drs-server | Telemetry retention policy enforcement |  | F | 3 | Per-variant Kafka consumers to TimescaleDB | B1.34 - per-class retention on hypertables; disk-full backpressure behaviour; operator alert. |
| drs-server | drs-server performance hardening |  | F + D | 10 | WebSocket fan-out hub, REST query endpoints | Weeks 12-17: harden to 2,000 msg/s SLA; query-latency budgets; async session-leak guard under sustained load. |
| drs-bridge | asyncio TCP server + stream reassembly |  | A | 4 | Contract artefact freeze | handle_client coroutine + stream-reassembly buffer (structurally fixes the legacy recv(4096)-without-buffer bug). |
| drs-bridge | drs-bridge runtime skeleton |  | A | 4 | asyncio TCP server + stream reassembly | Config + profile loader, parser ctypes loader, transport, Runtime, signal-handled main (B1.3 Phase 4). Shipped on main. |
| drs-bridge | ParserHandle ctypes wrapper |  | A | 3 | Parser ABI freeze | ctypes wrapper around the four-symbol C++ parser ABI. |
| drs-bridge | ResponseRouter + SessionRegistry |  | A | 6 | asyncio TCP server + stream reassembly, ParserHandle ctypes wrapper | Mode-switching from drs.session.control to RandomGenerator / ScenarioPublisherClient / HardwareRelay; per-hardware session state replacing the legacy global isRandom flag. |
| drs-bridge | RandomGenerator (Random mode) |  | A | 4 | ResponseRouter + SessionRegistry | Per-hardware random data within YAML-declared ranges; drs.control.<variant> topic for start/stop/config. |
| drs-bridge | ScenarioPublisherClient (Scenario mode) |  | A | 4 | ResponseRouter + SessionRegistry, Scenario publisher endpoint | HTTP client to SG scenario publisher; audit log of scenario-authoring operations. |
| drs-bridge | HardwareRelay (Integrated mode) |  | A | 5 | ResponseRouter + SessionRegistry, DRS instance addressing (per-instance transport) | TCP forward to entity-controller apps; entity-response consumption back into Kafka. |
| drs-bridge | DRS instance addressing (per-instance transport) |  | A | 6 | Roster publisher + presence + readiness reconcile | B1.43 Plan 1 - per-instance command servers, roster consumer, hot-reload diffing, framing-probation identity guard. Merged (PR #1). |
| drs-bridge | Hardware-config backend endpoints |  | A | 3 | DRS roster store + API | drs-server-side surface for G's IP/network-config panel (CRUD against roster). |
| drs-bridge | ICD codegen tool |  | A | 6 | First-variant C++ parser, Second/third variant parsers | Excel-ICD-to-C++/YAML/TypeScript skeleton generator; regression-diffed against hand-written variant 1; used from variant 3 onward. |
| C++ Parser Libraries | Parser ABI freeze |  | C | 3 |  | Freeze the 4-symbol ABI (extract_frame, parse_message, format_response, free_result) against drs-bridge/parsers/reference/. CRITICAL PATH (week 2). |
| C++ Parser Libraries | Common parser library |  | C | 4 | Parser ABI freeze | Shared frame_buffer, json_writer, header-scan helpers reused across variants. |
| C++ Parser Libraries | CMake build + ctypes verification |  | C | 2 | First-variant C++ parser | Shared-library (.dll) targets for Windows; Python ctypes binding verification. |
| C++ Parser Libraries | First-variant C++ parser |  | C | 5 | Parser ABI freeze, Common parser library | First IRS frame layout + golden-frame tests. CRITICAL PATH (weeks 1-4). |
| C++ Parser Libraries | Second/third variant parsers |  | C | 6 | First-variant C++ parser | parse_message bodies for priority variants 2-3. |
| C++ Parser Libraries | Variant parsers 4-6 |  | C | 9 | Second/third variant parsers, ICD codegen tool | parse_message + format_response for variants 4-6. |
| C++ Parser Libraries | Variant parsers 7-9 |  | C | 9 | Variant parsers 4-6 | parse_message for variants 7-9 per customer priority. |
| C++ Parser Libraries | Variant parsers 10-12 |  | C | 9 | Variant parsers 7-9 | Final priority-list variants; each documented with a golden-frame fixture. |
| C++ Parser Libraries | Legacy variant migration |  | C | 5 | First-variant C++ parser | Migrate legacy command.csv/structure.csv (SRX, MRX, GNSS, JSVUSHF) into the C++-parser model. |
| C++ Parser Libraries | Fuzz harness for extract_frame |  | C | 3 | Variant parsers 4-6 | Fuzz extract_frame against random input bytes across all variants (from week 9). |
| SG | STK Desktop UX review |  | B | 4 |  | Weeks 1-2: review STK Desktop placement/editing UX and improve SG discoverability where the embedded ActiveX env allows (ADR-016). |
| SG | Transmitter typed entity |  | B | 2 | Typed-entity DTO spec | DTO + view-model + WPF panel + IScenarioBackend methods + tests (~1.5 days). |
| SG | Receiver typed entity |  | B | 2 | Transmitter typed entity | Same typed-entity pattern as Transmitter. |
| SG | Antenna typed entity |  | B | 2 | Transmitter typed entity | Same typed-entity pattern as Transmitter. |
| SG | Scenario publisher endpoint |  | B | 4 | Transmitter typed entity | GET /exercises/{id}/responses?group_id&unit_id&tick returning pre-computed responses from computed_links; hosted from SG during execution. |
| SG | STK compute write-back pipeline |  | B | 8 | Scenario publisher endpoint | IScenarioBackend.ComputeLinks runs STK link-analysis tick-by-tick, batches results, writes computed_links to WS2 PostgreSQL over LAN. CRITICAL PATH. |
| SG | Scenario library lifecycle + edit-invalidation |  | B + F | 6 | STK compute write-back pipeline, EW Library UI | B1.19 - scenarios table state machine (NOT_COMPUTED/COMPUTED/STALE), partitioned content_json compute-input diff, immutable scenario_compute_snapshots, REPLACE-on-recompute. |
| SG | Telemetry filter/search/sort UI |  | B | 3 | SG-side UX wireframes | B1.10 - filter/search/sort controls for telemetry panels; per-operator persistence; export-filtered-rows. |
| SG | Telemetry display panels (FF/FH/Burst/Health) |  | B | 8 | WebSocket fan-out hub, SG-side UX wireframes, Telemetry filter/search/sort UI | WPF view-models per data class subscribing to drs-server WebSocket, rendered alongside the scenario globe. Not on critical path. |
| SG | Map Management import UI |  | B | 5 | SG-side UX wireframes | B1.5 - import dialog for Raster (JPEG/TIFF/GeoTIFF), Vector (Shape/KML), 3D (DTED dt0/dt1/dt2, DEM); STK layer registration; failure UX; per-scenario persistence. |
| SG | GIS toolset operator UI |  | B | 8 | SG-side UX wireframes | B1.6 - distance measurement, coordinate conversion (DMS/Decimal/IGRS), Line of Sight, Area Coverage, RLOS, layer manager, symbol library, FF/FH/Burst color coding. |
| SG | EW Library UI |  | B | 6 | SG-side UX wireframes | B1.7 - Emitter Library CRUD, Apriori Known Own/Enemy info base, emitter templates with versioning, library-to-scenario selection flow. |
| SG | Environment modelling config UI |  | B | 3 | SG-side UX wireframes | B1.8 - per-scenario precipitation/fog/atmospheric settings mapped to STK environment-model parameters. |
| SG | Exercise mode configuration UIs |  | B + A | 5 | SG-side UX wireframes | B1.9 - Random-mode parameter-range editor per variant, Scenario-mode computed-exercise picker, new-emitter-mid-planning flow. |
| SG | Integrated-mode readiness panel |  | B | 4 | Roster publisher + presence + readiness reconcile, SG-side UX wireframes | B1.43 Plan 3 - catalogue cache + /exercise/readiness panel showing per-instance configured/reachable/time_synced + roster drift. |
| SG | Reports panel + PDF template picker |  | B | 3 | PDF report generation, SG-side UX wireframes | B1.11 UI trigger - reports panel + PDF template picker driving E's WeasyPrint render. |
| SG | Recordings replay UI |  | B | 5 | SG-side UX wireframes | B1.12 - post-exercise replay: timeline scrubber, per-event log, GIS replay, telemetry replay. |
| SG | Log Management UI (4-class) |  | B + E | 5 | SG-side UX wireframes, RBAC + JWT auth | B1.13 - User/Sent-Message/Receive-Message/System log viewer with filter/sort/export; cross-link to DRS-side per-variant logs. |
| SG | DB Purge confirmation flow |  | B | 3 | SG-side UX wireframes | B1.14 - multi-step destructive-action UX: pre-purge backup prompt, two-step confirm, admin-only RBAC gate. |
| SG | Admin user/role management UI |  | B | 4 | RBAC + JWT auth, SG-side UX wireframes | Admin surface for user/role/feature/permission management; time-sync admin; DB backup/restore/purge entry points. |
| SG | STK lease-licence expiry handling |  | B + Ops | 2 |  | B1.35 - 30/7/1-day expiry warnings + day-366 renewal procedure; startup licence-reachability check. |
| SG | SG save/load + cold-start polish |  | B | 4 | Transmitter typed entity | Scenario file dialog, Save As .vdf with password, splash-window cold-start verification. |
| SG | SG UI automation harness |  | B | 4 | Telemetry display panels (FF/FH/Burst/Health) | B1.29 - FlaUI/Appium harness covering critical operator flows. |
| DRS Webapp | Webapp scaffold (React + Vite) |  | G | 3 | Contract artefact freeze | React-in-JavaScript (Vite, Vitest + RTL, SCSS) per ADR-018; hello-world SPA served by drs-server at /. Scaffold landed. |
| DRS Webapp | Webapp shell + auth flow |  | G | 5 | Webapp scaffold (React + Vite), RBAC + JWT auth | Login consuming E's JWT issuance; auth-guarded routes; landing dashboard; first live data card from one variant. |
| DRS Webapp | Per-variant monitor-scan views |  | G | 10 | Webapp shell + auth flow, WebSocket fan-out hub, DRS-side UX wireframes | Live message-rate via WebSocket; variant tab navigation; per-class message counters. Rolled out across variants in phases 3-6. |
| DRS Webapp | Message log viewer (Sent/Receive) |  | G | 6 | Webapp shell + auth flow, DRS-side UX wireframes | RFQ §F Manage Logs - per-variant Sent/Receive message logs with filter/sort/export. |
| DRS Webapp | IP / network configuration panel |  | G | 5 | Hardware-config backend endpoints, DRS-side UX wireframes | B1.43 Plan 3 - per-variant IP/network config CRUD against drs-server roster; YAML export/import surface. |
| DRS Webapp | Health detail view (LRU/subsystem/comm-link) |  | G | 4 | Consumer supervisor + health endpoints, DRS-side UX wireframes | RFQ §B - LRU + sub-system + communication-link health detail; Kafka consumer health at-a-glance. |
| DRS Webapp | Per-variant control surfaces |  | G | 4 | Per-variant monitor-scan views | Restart TCP server / parser via drs-server endpoints, with operator confirmation gates on disruptive actions. |
| DRS Webapp | Webapp accessibility pass |  | G | 3 | Per-variant monitor-scan views | Keyboard navigation + screen-reader labels for instructor environments. |
| DRS Webapp | Webapp e2e + coverage gate |  | G | 3 | Webapp shell + auth flow | B1.30 - Playwright smoke + Vitest coverage threshold. |
| DRS Webapp | Webapp checkJs type-safety decision |  | G + PL | 1 |  | B1.45 - decide editor-only vs enforced tsc gate vs status-quo for the JS DTO boundary. DECISION REQUIRED before Phase-6 surfaces. |
| Integration, Testing & Acceptance | Integration test rig (base) |  | D | 5 | CI bring-up harness | SDFC simulator + harness scaffolding at infrastructure/integration-tests/; drives one variant, then all priority variants. |
| Integration, Testing & Acceptance | Synthetic Kafka producer + multi-instance simulator |  | D | 4 | Integration test rig (base) | Load-test producer at configurable msg/s + N-concurrent-instance simulator (10/50/100) for capacity testing. |
| Integration, Testing & Acceptance | STK fixture scenarios |  | D + B | 3 | STK compute write-back pipeline | Pre-built .sc scenarios per compute path (point-to-point, area coverage, mobile entities) as deterministic compute-round-trip input. |
| Integration, Testing & Acceptance | Entity-controller app simulator |  | D + A | 3 | Integration test rig (base) | Simulate entity-workstation TCP endpoints for the Integrated-mode round-trip. |
| Integration, Testing & Acceptance | STK install diagnostic tool (stk-doctor) |  | D | 3 |  | B1.31 - env vars, COM registrations, host-present, licence-reachable checks. Needed before air-gapped install rehearsal. |
| Integration, Testing & Acceptance | Phase 1 gate - contracts |  | D | 2 | Contract artefact freeze, Parser ABI freeze | Week 2: parser ABI smoke green; OpenAPI validates against scaffold; Kafka topics + hypertables created and reachable. |
| Integration, Testing & Acceptance | Phase 2 gate - first end-to-end |  | D | 2 | Per-variant Kafka consumers to TimescaleDB, WebSocket fan-out hub, Webapp shell + auth flow, Integration test rig (base) | Week 5: single-variant SDFC-to-DB-to-UI round-trip <500ms p99, zero offset-before-write violations; webapp live card for same variant. |
| Integration, Testing & Acceptance | Phase 3 gate - Random mode + load |  | D | 2 | RandomGenerator (Random mode), Synthetic Kafka producer + multi-instance simulator, Per-variant monitor-scan views | Week 8: 4-variant Random mode + 1,000 msg/s sustained 10 min; zero consumer crashes; WS fan-out complete. |
| Integration, Testing & Acceptance | Phase 4 gate - Scenario mode + compute |  | D | 2 | STK compute write-back pipeline, ScenarioPublisherClient (Scenario mode), STK fixture scenarios | Week 11: compute-to-publish-to-DB-to-UI round-trip; 1,500 msg/s; Path 3 cross-LAN latency p99 <= 30 ms. |
| Integration, Testing & Acceptance | Phase 5 gate - Integrated mode |  | D | 2 | HardwareRelay (Integrated mode), Entity-controller app simulator | Week 13: 1-variant Integrated + Scenario concurrent; 9-12 variants total; Path 3 latency re-measured under Integrated load. |
| Integration, Testing & Acceptance | Air-gapped install rehearsal |  | D | 5 | Air-gap dependency vendoring process, WiX MSI installer + DVD packaging | Clean two-workstation VM deployment; DVD packaging dry-run (week 9 onward). |
| Integration, Testing & Acceptance | WiX MSI installer + DVD packaging |  | D | 8 | Air-gap dependency vendoring process | WiX/MSI installer consuming packages/ directly; DRS webapp built static assets shipped under drs-server webapp_static/; offline install verification. |
| Integration, Testing & Acceptance | Phase 6 gate - all variants + DVD install |  | D | 3 | Variant parsers 10-12, WiX MSI installer + DVD packaging, Air-gapped install rehearsal | Week 15: clean two-WS DVD install <90 min per WS, no manual fix-ups; webapp loads on first WS2 boot. |
| Integration, Testing & Acceptance | Security review + penetration testing |  | Sec | 10 | RBAC + JWT auth, Auth lifecycle endpoints | B1.28 - pen test, RBAC audit, input fuzzing, SQLi check (weeks 13-15; findings need remediation time). |
| Integration, Testing & Acceptance | WS1-WS2 partition resilience tests |  | B + F + A | 4 | WebSocket fan-out hub, STK compute write-back pipeline | B1.37 - reconnect/backoff, compute pause/resume, operator partition indicator (Phase 5). |
| Integration, Testing & Acceptance | Power-failure recovery tests |  | B + F | 3 | STK compute write-back pipeline | B1.38 - atomic compute batches; resume-or-discard on unclean restart (Phase 5/6). |
| Integration, Testing & Acceptance | Phase 7 gate - performance + acceptance |  | D + all | 5 | drs-server performance hardening, Phase 6 gate - all variants + DVD install | Week 17: 2,000 msg/s sustained >=30 min, query-latency budgets met; full cumulative suite + acceptance demo script passes. |
| Documentation & Delivery | SRS document |  | PL + AL | 15 | Detailed UX wireframes | B1.21 - RFQ M1 #1; drafted from the operator-playbook traceability matrix spine. Due end of Milestone-1. |
| Documentation & Delivery | ATP / STD / STR drafts |  | PL + D | 12 | Phase 4 gate - Scenario mode + compute | B1.22 - RFQ M2 #2; ATP draft wk12, customer sign-off wk14; STD/STR wks14-15. |
| Documentation & Delivery | User manuals |  | B + G + PL | 10 | SG-side UX wireframes, DRS-side UX wireframes | B1.23 - RFQ M2 #5; trainee-facing, from the operator playbook. Draft wk12, final wk17. |
| Documentation & Delivery | DVD install procedure (deployment guide) |  | D | 4 | Air-gapped install rehearsal | B1.32 - finalise deployment-guide §5 placeholder and rehearse. |
| Documentation & Delivery | Air-gapped maintenance/hotfix procedure |  | D + PL | 3 | DVD install procedure (deployment guide) | B1.33 - patch packaging, customer-IT approval, rollback. Maintenance handbook (wk16). |
| Documentation & Delivery | IRS document store + traceability |  | C + D | 3 |  | B1.24/B1.36 - IRS versioning store, IRS-to-parser traceability, build-time + runtime IRS-version stamping, IRS-revision change-management. |
| Documentation & Delivery | Third-party licence catalogue |  | D | 2 | Air-gap dependency vendoring process | B1.39 - MIT/Apache/BSD allow, GPL/AGPL/LGPL block; auto-generated, reviewed at each milestone gate. |
| Documentation & Delivery | Knowledge-transfer / handoff plan |  | PL | 5 | Phase 7 gate - performance + acceptance | B1.40 - customer team trained for warranty + IP handover; draft wk14, sit-with wks15-17. |
| Documentation & Delivery | Customer issue-reporting workflow |  | D + PL | 2 |  | B1.41 - air-gapped structured form + redacted log export + vendor tracker. |
| Documentation & Delivery | Customer clarifications bundle |  | PL + AL | 2 |  | B1.42 - resolve classroom topology (single/multi-SG), audit-log integrity, localisation, accessibility. Raise at design review. |

## Open decisions to resolve before / early in the build

- B1.4 - CC integration API surface: externally blocked on the client's Control Center requirements. Scope only the v2-decidable surface until the client responds.

- B1.44 - JVM licence for the Kafka runtime: OpenJDK/Temurin is GPLv2+Classpath-Exception vs the handbook's "GPL (all versions)" block-list. PL+D ruling needed before air-gap packaging.

- B1.45 - DRS webapp checkJs gate: editor-only vs enforced tsc vs status-quo. PL call before Phase-6 webapp surfaces.

- B1.15 - Blue/Red Line to entity-type mapping: needs an ADR before entity property panels.

- Variant count/priority list: parser & monitor-scan tasks are batched (first / 2-3 / 4-6 / 7-9 / 10-12); the actual list and ordering must come from the customer before per-variant durations are firm.

- STK dev-seat / licence count: tasks assume working STK 12.9 seats (procured separately) - confirm covered.

## Cross-cutting work surfaced as explicit tasks

- CI bring-up harness - org-hosted CI runners are currently paused (.github/disabled/ci.yml); integration suite runs locally for now.

- Polyrepo migration + release manifests - repository-and-release-strategy mandates the six-repo split + ewtss-release manifests.

- Air-gap dependency vendoring + WiX/DVD packaging - gate the Phase-6 install gate; vendoring becomes load-bearing after week 8.

- Build toolchain on the secure segment - build-from-source offline (vendored Node 22 + offline npm cache).

## Status caveat

Several rows are already partly/fully implemented in-repo and are listed for tracking, not fresh build: Time sync (B1.3), DRS roster store/publisher/reconcile/per-instance transport (B1.43), webapp scaffold, Kafka infra layer, reference parser template, security design + contracts scaffold. Mark these % complete or Closed on import rather than scheduling them anew.

## Zoho Projects import steps

- Projects > your project > Tasks > More (...) menu > Import > choose ewtss-v2-wbs-zoho.csv.

- Map columns: Task List > Task List; Task Name > Task Name; Parent Task > Parent Task (for subtasks); Owner > Owner/Assignee; Duration (days) > Duration; Dependency > Predecessor/Dependency; Description > Description.

- The file is UTF-8 and fully quoted. Hierarchy is expressed only via Task List + Parent Task; dependencies reference exact Task Names so they resolve on import.

- Apply the team-name mapping (owner legend above) before importing the Owner column.